## Sheet1
Developer | Fixer | CP | Part of System | Time took debugging | Issues and Fix
Ypark66 | Jshin79 | 1 | Paging init. | 30 minutes | Didn't enable the paging correctly. Fixed by enabling hardware (cr0 osdev).
Sha16 | Sha16 | 1 | RTC Write | 1 hour | Testing for RTC was not written properly could not refresh the rate. Error with rtc write.
Jshin79 | Jshin79 | 1 | PIC | 15 minutes | Forgot the osdev has order of arguments different than original (outb backwards).
Ypark66 | Jshin79 | 2 | Keyboard | 2 hours | Lots of the logics were written in python syntax (seriously). Fixed and debugged manually.
Ypark66 | Jshin79 | 2 | Keyboard Cursor | 30 minutes | Cursor would not reset on CTRL+L (clear screen) and would not follow through enter.
Ypark66 | Klee152 | 2 | Keyboard Buffer | 1 hour | Buffer overflow and refresh conditions were not correct
Klee152 | Sha16 | 2 | FileSystem | 30 minutes | Stuck in infinite loop. Switched while loop to for loop.
Klee152 | Jshin79/Sha16 | 2~3 | FileSystem | 2 hours | Problem with very large text file, condition case was filtering out the file that are too long
Sha16/Jshin79 | Sha16 | 3 | System Call Halt | 4 Hours | Pagefault whenever halting, error in paging structure as well as file system.
Sha16/Jshin79 | Jshin79 | 3~4 | System Call Halt Last Shell | 30minutes | Pagefault when exiting out of the last program(shell). Added condition case to relaunch.
Jshin79 | Jshin79 | 3 | System Call Execute | 1 Hour | Execute would take a hard coded input but would not take input from keyboard. Fixed keyboard buffer and execute structure.
Klee152 | Sha16 | 4 | System Call PingPong | 1 Hour | Various combined issues along with rtc initialization and rate was being set wrong.
Sha16 | Sha16 | 4 | System Call Grep/Cat | 1 Hour | Return Statement bypassing the if condition and always running. Badly formatted code issue
Group | Group | 4 | Fish/Vidmap | 5 hours+ | Issue within the paging structure causing page fault when vidmap structure is called[Unsolved]
Paging structure was originally written by the member who left the group right before cp2 deadline and as we were
heading toward the deadline it didn't seem reasonable to wipe out the paging structure to write a new one in a given frame of time just for fish.
Group | Sha16/Jshin79 | 5 | Multiple Terminal | 2 Hours | Extreme amount of page fault [Unsolved]
Klee152 | Klee152 | 5 | Multiple Terminal Switching Keyboard | 15 minutes | Alt+F1,F2,F3 not being registered properly. Set Alt+1,2,3 to switch terminal as temporary fix.

## ESRI_MAPINFO_SHEET (hidden)
DO NOT EDIT
For Esri use only